## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Anuj Tiwari
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2026-06-30
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | CampusNavigator – AI Powered College Discovery Platform
PROJECT ID | IP-11182
INTERN NAME | Anuj Tiwari
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
This Test Plan document defines the testing strategy, scope, objectives, methodology, schedule, and deliverables for the CampusNavigator web application developed during the internship period from 29 May 2026 to 28 June 2026. The application is a full-stack AI-powered college discovery platform built using React, Node.js, Express, and MongoDB. The purpose of testing is to ensure that the system functions correctly, securely, and efficiently across different devices and browsers while meeting both functional and non-functional requirements.
SCOPE
User Registration & Login (JWT Authentication) College Search & Filtering College Detail Page AI College Enrichment (Gemini Integration) AI Recommendation System College Comparison Feature Bookmark Functionality Application Tracker Admin Dashboard Review Moderation API Endpoints Testing Database CRUD Operations Responsive UI Testing Basic Security Testing
Third-party API internal logic (Google Gemini internal working) Hosting server infrastructure testing Load testing at enterprise scale Payment gateway integration (not applicable) External scraping source server validation
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
Ensure all features work as per defined requirements. Ensure secure authentication and authorization. Ensure accurate college data retrieval from database. Validate AI responses format and integration. Ensure responsive design across desktop and mobile. Ensure no critical or high-priority bugs remain before submission.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
Developer & Tester: Intern (Responsible for development and testing) Project Reviewer: Cloud Counselage Mentor Configuration Management: Git Version Control Deployment Responsibility: Intern
TEST METHODOLOGY
Agile-inspired iterative development methodology was followed. Features were developed in modules and tested individually before integration testing.
Unit Testing (Component & Function level) Integration Testing (Frontend + Backend API) System Testing (Complete application flow) Manual Functional Testing Basic Security Testing (JWT validation)
Bugs categorized as Critical, High, Medium, Low. Critical & High bugs fixed immediately. Medium & Low bugs fixed before final submission. Bugs tracked manually using issue checklist.
All core modules tested. 100% major functional flows verified. No Critical or High severity bugs pending. Application successfully tested before deployment.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan Document Test Case Sheet Bug Report Sheet Requirement Checklist Final Test Summary Report
RESOURCE AND ENVIRONMENT NEEDS
Google Chrome Browser Mozilla Firefox Postman (API Testing) MongoDB Atlas VS Code ESLint GitHub
OS: Windows 10/11 Node.js v18+ MongoDB Atlas Cloud Browser-based testing Localhost:5000 testing environment
Testing was conducted throughout the development lifecycle from 29 May 2026 to 28 June 2026 to ensure continuous quality validation.
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
User Registration | Verify user can register with valid details | 2026-06-02 | 2026-06-03 | Intern | Completed | Working correctly
Login Authentication | Verify JWT token generation | 2026-06-04 | 2026-06-05 | Intern | Completed | Token refresh working
College Search | Verify search by name/city | 2026-06-07 | 2026-06-08 | Intern | Completed | Debounce working
AI Enrichment | Verify AI returns structured data | 2026-06-12 | 2026-06-14 | Intern | Completed | JSON format validated
Recommendation System | Validate AI college matching | 2026-06-15 | 2026-06-17 | Intern | Completed | Match scores correct
Admin Panel | Verify CRUD operations | 2026-06-18 | 2026-06-20 | Intern | Completed | No issues
Dashboard | Validate charts & analytics | 2026-06-21 | 2026-06-22 | Intern | Completed | Data accurate
Final System Testing | Full application testing | 2026-06-25 | 2026-06-27 | Intern | Completed | Ready for submission
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features