## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Anuj Tiwari
PROJECT NAME: | CampusNavigator – AI Powered College Discovery Platform
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-06-30
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | CampusNavigator – AI Powered College Discovery Platform
PROJECT ID | IP-11182
PROJECT MANAGER | Cloud Counselage Mentor
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2026-06-02 | Initial difficulty in designing scalable folder structure for full-stack application. | Technical / Architecture | Yes | Plan folder structure before starting development. Follow modular architecture. | Refactored project into separate frontend and backend structure. | Intern | Solved | Improved maintainability and scalability.
2 | 2026-06-05 | JWT authentication errors due to improper token refresh handling. | Security | Yes | Implement proper token refresh logic and axios interceptors. | Added automatic token refresh mechanism. | Intern | Solved | Authentication flow became stable.
3 | 2026-06-09 | Search feature causing performance lag due to continuous API calls. | Performance | Yes | Use debounce mechanism to reduce API calls. | Implemented useDebounce hook for search input. | Intern | Solved | Performance significantly improved.
4 | 2026-06-12 | AI response format inconsistent while integrating Gemini API. | AI Integration | Yes | Use structured JSON prompts and response validation. | Modified prompt engineering and added response parsing validation. | Intern | Solved | AI integration became reliable.
5 | 2026-06-16 | UI responsiveness issues on smaller screen devices. | UI/UX | Yes | Use responsive Tailwind utilities and test on multiple devices. | Updated layout with mobile-first approach. | Intern | Solved | Improved mobile compatibility.
6 | 2026-06-18 | MongoDB schema mismatch causing data validation errors. | Database | No | Define strict schema validation rules. | Updated Mongoose schema with required fields and validation. | Intern | Solved | Data consistency improved.
7 | 2026-06-22 | Difficulty in managing multiple state updates across components. | State Management | Yes | Use centralized state management (Zustand). | Refactored state logic into dedicated stores. | Intern | Solved | Code became cleaner and modular.
8 | 2026-06-26 | Final testing revealed minor UI inconsistencies and edge case bugs. | Testing | Yes | Conduct complete system testing before final deployment. | Performed full regression testing and fixed minor issues. | Intern | Solved | Application ready for submission.