## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | CampusNavigator – AI Powered College Discovery Platform
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-05-29
EXPECTED COMPLETION DATE | 2026-06-28
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To design and develop a centralized AI-powered web application that enables students in India to search, compare, and explore colleges with detailed information including courses, admissions, placements, and AI-driven recommendations using modern full-stack technologies.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Currently, students lack a centralized, reliable, and user-friendly platform for discovering colleges with accurate and structured information. Existing platforms are scattered and advertisement-driven. CampusNavigator provides a structured, AI-powered solution that improves accessibility, decision-making, and user experience, thereby addressing the identified problem effectively.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Successfully develop full-stack web application. Integrate AI recommendation and chatbot features. Implement secure JWT authentication. Seed database with 100+ real Indian colleges. Ensure 100% core module functionality before submission. Complete project within timeline (29 May – 28 June 2026).
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | Fully functional web application (Frontend + Backend) Admin Panel AI Chatbot Integration AI Recommendation System Database with seeded colleges Project Documentation Test Plan & Test Reports Deployment-ready build
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | User Registration & Login College Search & Filters College Detail Page AI Enrichment AI Recommendations College Comparison Dashboard & Application Tracker Admin Panel Review Moderation Responsive UI Basic Security Implementation
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Payment Integration Enterprise-scale load testing Native mobile application Multi-language support Large-scale production hosting
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Intern (Web development)- Me 1 Project Mentor (Reviewer)
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | VS Code IDE MongoDB Atlas Google Gemini API GitHub Node.js & NPM Cloudinary (optional image storage)
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Internship academic project. Infrastructure cost covered under free-tier services: MongoDB Atlas (Free Tier) Gemini API (Free Tier) Local development environment Total Estimated Cost: Minimal / N.A.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Me and Cloud Counselage Pvt. Ltd.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Cloud Counselage Mentor Internship Evaluation Team Prospective Students (End Users) Admin Users
END CUSTOMER (Mention the client name.) | Students seeking college information in India
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | AI API downtime MongoDB connectivity issues Time constraint (30-day deadline) Integration bugs between frontend and backend Learning curve for AI prompt engineering
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | Stable internet connection available. Free-tier API limits sufficient for development. Required technologies available and supported. Internship duration fixed (29 May – 28 June 2026).
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 30-day development timeline. Individual project (single developer). Limited infrastructure budget. Academic submission deadline.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Completion Date: 31-May-2026
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Completion Date: 02-June-2026
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 06-June-2026
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 22-June-2026
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Completion Date: 27-June-2026
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Completion Date: 28-June-2026
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Completion Date: 30-June-2026